## Dashboard
Project Plan Dashboard
A live summary of progress, schedule, budget, task status, and project risk.
Website Redesign & Launch | [7 empty] | Project Manager: Daniel Brooks • Aug 24–Oct 30, 2026
Total tasks |  | Completed |  | Overall progress |  | Overdue tasks |  | Approved budget |  | Actual spend | Budget remaining
19 |  | 2 |  | 9.468% |  | 0 |  | 180000 |  | 75300 | 104700
Task status | Count | [5 empty] | Risk priority | Count
Not Started | 15 | [5 empty] | CRITICAL | 2
In Progress | 2 | [5 empty] | HIGH | 3
Blocked | 0 | [5 empty] | MEDIUM | 2
Done | 2 | [5 empty] | LOW | 0
Total | 19 | [5 empty] | Open items | 7
Milestone | Target Date | Owner | Status | Days Remaining | Flag |  | Category | Planned | Actual
Discovery complete | 2026-09-04 | James Wilson | Upcoming | 12 | ON TRACK |  | Labor | 129000 | 63200
Design approved | 2026-09-18 | Aisha Khan | Upcoming | 26 | ON TRACK |  | Content | 13000 | 3100
Development complete | 2026-10-09 | Marcus Lee | Upcoming | 47 | ON TRACK |  | Software | 6500 | 6200
QA signoff | 2026-10-21 | Nina Garcia | Upcoming | 59 | ON TRACK |  | Infrastructure | 8500 | 2800
Content approved | 2026-10-23 | Emily Chen | Upcoming | 61 | ON TRACK |  | External | 9000 | 0
Production launch | 2026-10-30 | Daniel Brooks | Upcoming | 68 | ON TRACK
Formulas:
Status = IF([Count]="","",IF([Count]<TODAY(),"Past Due","Upcoming"))
Overall progress = IF([Count]="","",[Count]-TODAY())
Flag = IF([Count]="","",IF([Count]<TODAY(),"OVERDUE",IF([Count]<=TODAY()+7,"DUE SOON","ON TRACK")))

## Project Setup
Project Setup
Define the project, dates, budget, goals, team, and planning assumptions.
Replace the sample information in orange cells. Other worksheets reference these project details automatically.
Project details |  | Project objective
Project Name | Website Redesign & Launch | Redesign the company website to improve conversion, clarify product positioning, strengthen organic search visibility, and launch before the Q4 campaign begins.
Project Manager | Daniel Brooks
Executive Sponsor | Maya Thompson
Project Status | In Progress
Start Date | 2026-08-24
Target End Date | 2026-10-30 | Team Member | Role | Department | Milestone | Target Date | Owner
Approved Budget | 180000 | Daniel Brooks | Project Manager | PMO | Discovery complete | 2026-09-04 | James Wilson
Working Days / Week | 5 | Aisha Khan | Product Designer | Design | Design approved | 2026-09-18 | Aisha Khan
Reporting Frequency | Weekly | Marcus Lee | Frontend Developer | Engineering | Development complete | 2026-10-09 | Marcus Lee
|  | Sofia Patel | Backend Developer | Engineering | QA signoff | 2026-10-21 | Nina Garcia
|  | Nina Garcia | QA Engineer | Engineering | Content approved | 2026-10-23 | Emily Chen
|  | Omar Hassan | Marketing Manager | Marketing | Production launch | 2026-10-30 | Daniel Brooks
|  | Emily Chen | Content Strategist | Marketing
|  | James Wilson | Business Analyst | Operations

## Task Plan
Project Task Plan
Plan tasks, owners, dates, effort, progress, costs, and schedule health in one table.
Enter or replace orange cells. Duration, cost variance, days remaining, and schedule flag calculate automatically.
WBS | Phase | Task | Owner | Priority | Status | Start Date | Due Date | Duration (Days) | % Complete | Planned Hours | Actual Hours | Budgeted Cost | Actual Cost | Cost Variance | Days Remaining | Schedule Flag | Notes
1.1 | Initiation | Confirm project scope | Daniel Brooks | High | Done | 2026-08-24 | 2026-08-25 | 2 | 100% | 12 | 12 | 1800 | 1750 | 50 | 2 | DONE | Approved by sponsor.
1.2 | Initiation | Identify stakeholders | Daniel Brooks | Medium | Done | 2026-08-24 | 2026-08-26 | 3 | 100% | 8 | 8 | 1200 | 1200 | 0 | 3 | DONE | Core reviewers confirmed.
2.1 | Discovery | Review analytics and conversion data | James Wilson | High | In Progress | 2026-08-26 | 2026-09-01 | 7 | 80% | 24 | 20 | 2600 | 2200 | 400 | 9 | ON TRACK | Checkout funnel requires attention.
2.2 | Discovery | Run stakeholder interviews | James Wilson | High | In Progress | 2026-08-27 | 2026-09-03 | 8 | 65% | 30 | 24 | 3300 | 2700 | 600 | 11 | ON TRACK | Six of eight interviews complete.
2.3 | Discovery | Finalize requirements | Daniel Brooks | Critical | Not Started | 2026-09-02 | 2026-09-04 | 3 | 0% | 18 | 0 | 2700 | 0 | 2700 | 12 | ON TRACK | Depends on interviews.
3.1 | UX & Design | Create sitemap and user flows | Aisha Khan | High | Not Started | 2026-09-03 | 2026-09-08 | 6 | 0% | 28 | 0 | 3500 | 0 | 3500 | 16 | ON TRACK
3.2 | UX & Design | Build low-fidelity wireframes | Aisha Khan | High | Not Started | 2026-09-07 | 2026-09-11 | 5 | 0% | 32 | 0 | 4000 | 0 | 4000 | 19 | ON TRACK
3.3 | UX & Design | Create high-fidelity designs | Aisha Khan | Critical | Not Started | 2026-09-10 | 2026-09-17 | 8 | 0% | 46 | 0 | 5750 | 0 | 5750 | 25 | ON TRACK
3.4 | UX & Design | Approve design system | Daniel Brooks | High | Not Started | 2026-09-17 | 2026-09-18 | 2 | 0% | 10 | 0 | 1500 | 0 | 1500 | 26 | ON TRACK | Milestone approval.
4.1 | Development | Build reusable page components | Marcus Lee | Critical | Not Started | 2026-09-16 | 2026-09-29 | 14 | 0% | 70 | 0 | 8400 | 0 | 8400 | 37 | ON TRACK
4.2 | Development | Implement CMS and integrations | Sofia Patel | Critical | Not Started | 2026-09-21 | 2026-10-02 | 12 | 0% | 64 | 0 | 8000 | 0 | 8000 | 40 | ON TRACK
4.3 | Development | Develop page templates | Marcus Lee | High | Not Started | 2026-09-28 | 2026-10-07 | 10 | 0% | 58 | 0 | 6960 | 0 | 6960 | 45 | ON TRACK
4.4 | Development | Performance and accessibility pass | Marcus Lee | High | Not Started | 2026-10-05 | 2026-10-09 | 5 | 0% | 30 | 0 | 3600 | 0 | 3600 | 47 | ON TRACK
5.1 | Content | Refresh website copy | Emily Chen | High | Not Started | 2026-09-14 | 2026-10-02 | 19 | 0% | 52 | 0 | 4160 | 0 | 4160 | 40 | ON TRACK
5.2 | Content | Prepare SEO metadata and redirects | Omar Hassan | High | Not Started | 2026-09-28 | 2026-10-12 | 15 | 0% | 34 | 0 | 3400 | 0 | 3400 | 50 | ON TRACK
6.1 | Testing | Functional and regression testing | Nina Garcia | Critical | Not Started | 2026-10-08 | 2026-10-16 | 9 | 0% | 44 | 0 | 4400 | 0 | 4400 | 54 | ON TRACK
6.2 | Testing | User acceptance testing | James Wilson | High | Not Started | 2026-10-15 | 2026-10-21 | 7 | 0% | 28 | 0 | 3080 | 0 | 3080 | 59 | ON TRACK
7.1 | Launch | Production deployment | Sofia Patel | Critical | Not Started | 2026-10-26 | 2026-10-29 | 4 | 0% | 20 | 0 | 2500 | 0 | 2500 | 67 | ON TRACK
7.2 | Launch | Launch validation and handoff | Daniel Brooks | Critical | Not Started | 2026-10-30 | 2026-10-30 | 1 | 0% | 12 | 0 | 1800 | 0 | 1800 | 68 | ON TRACK | Launch milestone.
Formulas:
Days Remaining = IF(OR([Task]="",[Due Date]=""),"",[Due Date]-TODAY())
Schedule Flag = IF([Task]="","",IF([Status]="Done","DONE",IF(AND([Due Date]<TODAY(),J6<1),"OVERDUE",IF(AND([Due Date]<=TODAY()+7,J6<1),"DUE SOON","ON TRACK"))))

## Timeline
Project Timeline
A formula-driven daily Gantt view linked to the Project Task Plan.
The timeline updates when Start Date, Due Date, or % Complete changes in Task Plan. Dark blue shows completed progress; light blue shows remaining planned duration.
WBS | Task | Owner | Status | Start | Due | % Complete | Days | time axis 2026-08-24 to 2026-10-30
1.1 | Confirm project scope | Daniel Brooks | Done | 2026-08-24 | 2026-08-25 | 100% | 2 | 2026-08-24: 2; 2026-08-25: 2
1.2 | Identify stakeholders | Daniel Brooks | Done | 2026-08-24 | 2026-08-26 | 100% | 3 | 2026-08-24: 2; 2026-08-25: 2; 2026-08-26: 2
2.1 | Review analytics and conversion data | James Wilson | In Progress | 2026-08-26 | 2026-09-01 | 80% | 7 | 2026-08-26: 2; 2026-08-27: 2; 2026-08-28: 2; 2026-08-29: 2; 2026-08-30: 2; 2026-08-31: 2; 2026-09-01: 1
2.2 | Run stakeholder interviews | James Wilson | In Progress | 2026-08-27 | 2026-09-03 | 65% | 8 | 2026-08-27: 2; 2026-08-28: 2; 2026-08-29: 2; 2026-08-30: 2; 2026-08-31: 2; 2026-09-01: 2; 2026-09-02: 1; 2026-09-03: 1
2.3 | Finalize requirements | Daniel Brooks | Not Started | 2026-09-02 | 2026-09-04 |  | 3 | 2026-09-02: 2; 2026-09-03: 1; 2026-09-04: 1
3.1 | Create sitemap and user flows | Aisha Khan | Not Started | 2026-09-03 | 2026-09-08 |  | 6 | 2026-09-03: 2; 2026-09-04: 1; 2026-09-05: 1; 2026-09-06: 1; 2026-09-07: 1; 2026-09-08: 1
3.2 | Build low-fidelity wireframes | Aisha Khan | Not Started | 2026-09-07 | 2026-09-11 |  | 5 | 2026-09-07: 2; 2026-09-08: 1; 2026-09-09: 1; 2026-09-10: 1; 2026-09-11: 1
3.3 | Create high-fidelity designs | Aisha Khan | Not Started | 2026-09-10 | 2026-09-17 |  | 8 | 2026-09-10: 2; 2026-09-11: 1; 2026-09-12: 1; 2026-09-13: 1; 2026-09-14: 1; 2026-09-15: 1; 2026-09-16: 1; 2026-09-17: 1
3.4 | Approve design system | Daniel Brooks | Not Started | 2026-09-17 | 2026-09-18 |  | 2 | 2026-09-17: 2; 2026-09-18: 1
4.1 | Build reusable page components | Marcus Lee | Not Started | 2026-09-16 | 2026-09-29 |  | 14 | 2026-09-16: 2; 2026-09-17: 1; 2026-09-18: 1; 2026-09-19: 1; 2026-09-20: 1; 2026-09-21: 1; 2026-09-22: 1; 2026-09-23: 1; 2026-09-24: 1; 2026-09-25: 1; 2026-09-26: 1; 2026-09-27: 1; 2026-09-28: 1; 2026-09-29: 1
4.2 | Implement CMS and integrations | Sofia Patel | Not Started | 2026-09-21 | 2026-10-02 |  | 12 | 2026-09-21: 2; 2026-09-22: 1; 2026-09-23: 1; 2026-09-24: 1; 2026-09-25: 1; 2026-09-26: 1; 2026-09-27: 1; 2026-09-28: 1; 2026-09-29: 1; 2026-09-30: 1; 2026-10-01: 1; 2026-10-02: 1
4.3 | Develop page templates | Marcus Lee | Not Started | 2026-09-28 | 2026-10-07 |  | 10 | 2026-09-28: 2; 2026-09-29: 1; 2026-09-30: 1; 2026-10-01: 1; 2026-10-02: 1; 2026-10-03: 1; 2026-10-04: 1; 2026-10-05: 1; 2026-10-06: 1; 2026-10-07: 1
4.4 | Performance and accessibility pass | Marcus Lee | Not Started | 2026-10-05 | 2026-10-09 |  | 5 | 2026-10-05: 2; 2026-10-06: 1; 2026-10-07: 1; 2026-10-08: 1; 2026-10-09: 1
5.1 | Refresh website copy | Emily Chen | Not Started | 2026-09-14 | 2026-10-02 |  | 19 | 2026-09-14: 2; 2026-09-15: 1; 2026-09-16: 1; 2026-09-17: 1; 2026-09-18: 1; 2026-09-19: 1; 2026-09-20: 1; 2026-09-21: 1; 2026-09-22: 1; 2026-09-23: 1; 2026-09-24: 1; 2026-09-25: 1; 2026-09-26: 1; 2026-09-27: 1; 2026-09-28: 1; 2026-09-29: 1; 2026-09-30: 1; 2026-10-01: 1; 2026-10-02: 1
5.2 | Prepare SEO metadata and redirects | Omar Hassan | Not Started | 2026-09-28 | 2026-10-12 |  | 15 | 2026-09-28: 2; 2026-09-29: 1; 2026-09-30: 1; 2026-10-01: 1; 2026-10-02: 1; 2026-10-03: 1; 2026-10-04: 1; 2026-10-05: 1; 2026-10-06: 1; 2026-10-07: 1; 2026-10-08: 1; 2026-10-09: 1; 2026-10-10: 1; 2026-10-11: 1; 2026-10-12: 1
6.1 | Functional and regression testing | Nina Garcia | Not Started | 2026-10-08 | 2026-10-16 |  | 9 | 2026-10-08: 2; 2026-10-09: 1; 2026-10-10: 1; 2026-10-11: 1; 2026-10-12: 1; 2026-10-13: 1; 2026-10-14: 1; 2026-10-15: 1; 2026-10-16: 1
6.2 | User acceptance testing | James Wilson | Not Started | 2026-10-15 | 2026-10-21 |  | 7 | 2026-10-15: 2; 2026-10-16: 1; 2026-10-17: 1; 2026-10-18: 1; 2026-10-19: 1; 2026-10-20: 1; 2026-10-21: 1
7.1 | Production deployment | Sofia Patel | Not Started | 2026-10-26 | 2026-10-29 |  | 4 | 2026-10-26: 2; 2026-10-27: 1; 2026-10-28: 1; 2026-10-29: 1
7.2 | Launch validation and handoff | Daniel Brooks | Not Started | 2026-10-30 | 2026-10-30 |  | 1 | 2026-10-30: 2

## Budget
Project Budget
Compare planned, committed, and actual costs by project category.
Enter planned, committed, and actual amounts in orange cells. Remaining budget and variance calculate automatically.
Category | Cost Item | Owner | Planned Budget | Committed | Actual Cost | Budget Remaining | Variance % | Budget Status | Notes | Budget metric | Value
Labor | Project management | Daniel Brooks | 18000 | 15000 | 14800 | 3200 | 17.78% | ON TRACK |  | Approved Budget | 180000
Labor | Discovery and analysis | James Wilson | 12000 | 9800 | 8600 | 3400 | 28.33% | ON TRACK |  | Planned Budget | 180000
Labor | UX and visual design | Aisha Khan | 23000 | 19000 | 15200 | 7800 | 33.91% | ON TRACK |  | Actual Cost | 75300
Labor | Frontend development | Marcus Lee | 32000 | 26000 | 12400 | 19600 | 61.25% | ON TRACK |  | Remaining | 104700
Labor | Backend development | Sofia Patel | 28000 | 22000 | 9800 | 18200 | 65% | ON TRACK
Labor | QA and testing | Nina Garcia | 16000 | 9000 | 2400 | 13600 | 85% | ON TRACK
Content | Copy and SEO | Emily Chen | 13000 | 8500 | 3100 | 9900 | 76.15% | ON TRACK
Software | Design and testing tools | Daniel Brooks | 6500 | 6200 | 6200 | 300 | 4.615% | ON TRACK
Infrastructure | Hosting and deployment | Sofia Patel | 8500 | 7000 | 2800 | 5700 | 67.06% | ON TRACK
External | Accessibility audit | Daniel Brooks | 9000 | 9000 | 0 | 9000 | 100% | ON TRACK
Contingency | Project contingency | Daniel Brooks | 14000 | 0 | 0 | 14000 | 100% | ON TRACK

## Risks & Issues
Risks & Issues
Log project risks and active issues, score severity, assign owners, and track mitigation.
Probability × Impact produces the risk score. Priority and days open calculate automatically.
Type | ID | Description | Owner | Probability | Impact | Score | Priority | Status | Mitigation / Next Step | Created Date | Due Date | Days Open
Risk | R-001 | Content approval may delay development handoff | Emily Chen | 4 | 4 | 16 | CRITICAL | Open | Create an approval calendar and named backup reviewer. | 2026-08-17 | 2026-09-11 | 6
Risk | R-002 | Legacy CMS integration may require additional work | Sofia Patel | 3 | 5 | 15 | CRITICAL | Open | Complete a technical spike before component development. | 2026-08-18 | 2026-09-04 | 5
Risk | R-003 | Accessibility audit could identify late design changes | Aisha Khan | 3 | 4 | 12 | HIGH | Monitoring | Review accessibility during wireframes and design QA. | 2026-08-18 | 2026-09-18 | 5
Issue | I-001 | Analytics event naming is not finalized | Omar Hassan | 4 | 3 | 12 | HIGH | In Progress | Hold a working session with marketing and engineering. | 2026-08-19 | 2026-09-02 | 4
Risk | R-004 | Stakeholder availability may slow approvals | Daniel Brooks | 3 | 3 | 9 | MEDIUM | Monitoring | Send approvals 48 hours early and track alternates. | 2026-08-20 | 2026-09-18 | 3
Issue | I-002 | Two redirect owners remain unassigned | Omar Hassan | 2 | 3 | 6 | MEDIUM | Open | Assign redirect groups during the next content review. | 2026-08-21 | 2026-09-08 | 2
Risk | R-005 | Launch window overlaps another infrastructure change | Sofia Patel | 2 | 5 | 10 | HIGH | Monitoring | Confirm the change freeze with infrastructure leads. | 2026-08-22 | 2026-10-09 | 1
Formulas:
Days Open = IF(OR([ID]="",[Created Date]=""),"",IF([Status]="Closed","",TODAY()-[Created Date]))

## Start Here
Start Here
A quick guide to using the free KolApp project plan template for Excel.
This workbook connects project scope, tasks, timeline, budget, milestones, and risk in one editable plan.
Step | What to do | Workbook map
1. Set up the project | Replace the sample details, objective, team, and milestones on Project Setup. | Dashboard | Project health summary | Formula-driven
2. Build the task plan | Add phases and tasks, then assign owners, dates, effort, progress, and costs. | Project Setup | Project details, team, milestones | Editable
3. Review the timeline | Use Timeline to see overlapping work and the formula-driven Gantt bars. | Task Plan | Tasks, owners, dates, effort, costs | Mixed
4. Manage the budget | Enter planned, committed, and actual costs by category or cost item. | Timeline | Daily Gantt view | Formula-driven
5. Track risks and issues | Score probability and impact, assign owners, and document mitigation steps. | Budget | Planned, committed, and actual cost | Mixed
6. Monitor the dashboard | Review task progress, budget, milestones, risks, and schedule health each week. | Risks & Issues | Risk scoring and mitigation | Mixed
7. Keep it current | Update the workbook whenever dates, owners, costs, status, or risks change. | Start Here | Instructions and formula guide | Reference
Important |  | Color guide
Keep task dates and completion percentages current. The dashboard and Gantt timeline depend on those fields. |  | Editable input | Calculated automatically